## Sheet1
id | description | purpose | severity_after_mitigation | likelihood_after_mitigation | detectability_after_mitigation | input | expected_output
1 | Temperature alarm test | Verify alarm function for overtemperature | 2 | 1 | 1 | Simulate temperature above limit | Alarm active within 1s
2 | Tightness test | Check vessel tightness | 3 | 1 | 1 | Pressurize to 1.5 bar | No pressure drop after 30 min
3 | Calibration test | Verify sensor accuracy | 2 | 1 | 1 | Reference measurement with calibrated instruments | Deviation < +/-1%
4 | UPS test | Check uninterruptible power supply | 2 | 1 | 1 | Simulate grid disconnection | System runs 30 min on UPS
5 | Audit trail test | Verify audit trail function | 3 | 1 | 1 | Perform parameter change | Change logged with timestamp and user
6 | Access control test | Check user management | 3 | 1 | 1 | Login attempts with different roles | Access according to permission level
7 | Safety inspection | Check mechanical safety devices | 3 | 1 | 1 | Visual inspection and function test | All safety devices functional
8 | CIP validation | Verify cleaning effectiveness | 3 | 1 | 1 | Perform CIP cycle | TOC < 10 ppm after cleaning
9 | Pressure safety test | Check overpressure protection | 3 | 1 | 1 | Build pressure until safety valve triggers | Valve opens at set pressure +/-5%
10 | Network redundancy test | Check network failover | 2 | 1 | 1 | Disconnect primary connection | Switchover to backup within 5s
11 | Alarm test | Verify all alarm messages | 2 | 1 | 1 | Simulate all alarm conditions | Correct alarm message and logging
12 | Recipe locking test | Check recipe change lock | 2 | 1 | 1 | Attempt recipe change during batch | Change is prevented
13 | SIP validation | Verify sterilization | 3 | 1 | 1 | SIP cycle with bioindicators | All bioindicators negative
14 | Document review | Completeness check of documentation | 2 | 1 | 1 | Review all documents | All required documents present
15 | Performance test | Check production performance | 2 | 1 | 1 | 3 consecutive production runs | All batches within specification